## Dashboard
PROJECT PROGRESS DASHBOARD
Prepared for Directors' Review
PROJECT OVERVIEW
Project Name: | E-commerce RaasPal | Project Manager: | Branny
Start Date: | 2026-07-02 | Target End Date: | 2026-08-14
Report Date: | 2026-07-21 | Days Remaining: | 24
KEY METRICS
Overall Progress |  | Tasks Completed |  | Needs Attention | Overall Status
70.83% |  | 7 / 12 |  | 0 | On Track
PROGRESS BY PHASE
Phase | % Complete | Status
Planning | 100% | Complete
Design | 100% | Complete
Development | 84% | On Track
Testing | 12.5% | On Track
Launch | 5% | On Track
UPCOMING MILESTONES
Milestone | Target Date | Status
Requirements & scope sign-off | 2026-06-20 | Complete
Design system & rebrand approved | 2026-07-08 | Complete
Storefront + checkout feature-complete | 2026-07-20 | Complete
Admin panel + orders management done | 2026-07-25 | Complete
Payment integration live (Omise) | 2026-08-15 | On Track
Production launch / Go-live | 2026-09-30 | On Track
KEY RISKS (OPEN / MONITORING)
Description | Severity | Status
Omise/Opn merchant account not yet approved — blocks online card & PromptPay payments | High | Open
Legal/policy pages missing (PDPA Privacy, Terms, Refund, Shipping) | High | Open
Sokochan fulfilment API not yet integrated — fulfilment manual at launch | Medium | Monitoring
SEO & branding assets incomplete (sitemap, robots, OG tags, favicon) | Medium | Open
Brand name not finalized — affects domain, meta, logo, legal entity | Medium | Monitoring
Formulas:
E-commerce RaasPal = MIN(TaskTracker[Start Date])
E-commerce RaasPal = INDEX(Milestones[Target Date],1)
Branny = MAX(TaskTracker[End Date])

## Task Tracker
PROJECT TASK TRACKER
Update % Complete and dates below — Status updates automatically
Task ID | Task Name | Phase | Owner | Start Date | End Date | Duration (Days) | % Complete | Status | Notes
1 | Requirements, tech stack & vendor selection | Planning | Branny | 2026-07-02 | 2026-07-04 | 3 | 100% | Complete | Confirmed: Next.js, Supabase, Omise, Vercel, Sokochan
2 | Reference research & PRD | Planning | Branny | 2026-07-04 | 2026-07-05 | 2 | 100% | Complete | Robomate Australia used as the structural reference
3 | Brand rebrand & design system | Design | Branny | 2026-07-06 | 2026-07-10 | 5 | 100% | Complete | CEO approved forest-green + gold theme (Jul 8)
4 | Storefront & product-page UX design | Design | Branny | 2026-07-13 | 2026-07-14 | 2 | 100% | Complete | Hero category chips + product detail layout
5 | Storefront build (home, shop, product, search) | Development | Branny | 2026-07-15 | 2026-07-16 | 2 | 100% | Complete | Bilingual EN/TH, dark mode, product search
6 | Cart, checkout & server-side orders | Development | Branny | 2026-07-17 | 2026-07-17 | 1 | 100% | Complete | Server reprices every line; guest checkout supported
7 | Auth, customer accounts & admin panel | Development | Branny | 2026-07-17 | 2026-07-17 | 1 | 100% | Complete | Supabase auth; product CRUD, orders dashboard, hide/show
8 | Payment integration (Omise / Opn) | Development | Branny | 2026-07-16 | TBD | TBD | 40% | Unscheduled | Card+3DS+webhook built; PAUSED for Omise account. Contact-to-pay live
9 | QA, i18n & launch hardening (SEO, legal, branding) | Testing | Branny | TBD | TBD | TBD | 20% | Unscheduled | Sitemap/robots/OG, PDPA legal pages, favicon
10 | Production deployment & go-live | Launch | Branny | 2026-08-07 | 2026-08-14 | 8 | 5% | On Track | Deploy to Vercel with live keys; register webhook
11 | Sokochan API Integration | Development | Branny | 2026-07-21 | 2026-07-25 | 5 | 80% | On Track | Integrate with fulfillment company's api so that the ordering function is smooth after customer checkout
10 | UAT | Testing | Branny | TBD | TBD | TBD | 5% | Unscheduled | Deploy to Vercel with live keys; register webhook
Formulas:
Status = IF(H4=1,"Complete",IF(NOT(ISNUMBER([End Date])),"Unscheduled",IF(AND([End Date]<TODAY(),H4<1),"Delayed",IF(([End Date]-TODAY())<=3,"At Risk","On Track"))))

## Milestones
PROJECT MILESTONES
Key deliverables and target dates — Status updates automatically
ID | Milestone | Phase | Target Date | Actual Date | Owner | Status | Notes
1 | Requirements & scope sign-off | Planning | 2026-06-20 | 2026-06-20 | Branny | Complete | Tech stack + PRD approved
2 | Design system & rebrand approved | Design | 2026-07-08 | 2026-07-08 | Branny | Complete | Forest-green + gold; CEO sign-off
3 | Storefront + checkout feature-complete | Development | 2026-07-20 | 2026-07-20 | Branny | Complete | Cart, checkout, server-side orders working
4 | Admin panel + orders management done | Development | 2026-07-25 | 2026-07-21 | Branny | Complete | Products, orders dashboard, visibility toggle
5 | Payment integration live (Omise) | Development | 2026-08-15 |  | Branny | On Track | Blocked on Omise merchant-account approval
6 | Production launch / Go-live | Launch | 2026-09-30 |  | Branny | On Track | Public launch to customers
7 | UAT | Testing | TBD |  | Branny | Unscheduled | Blocked on Omise merchant-account approval
Formulas:
Status = IF([Actual Date]<>"","Complete",IF(NOT(ISNUMBER([Target Date])),"Unscheduled",IF([Target Date]<TODAY(),"Delayed",IF(([Target Date]-TODAY())<=7,"At Risk","On Track"))))

## Risks & Issues
RISKS & ISSUES LOG
Track risks, severity, and mitigation plans
ID | Description | Category | Severity | Likelihood | Owner | Mitigation Plan | Status | Date Raised
1 | Omise/Opn merchant account not yet approved — blocks online card & PromptPay payments | Technical | High | Likely | Branny | Finish Omise signup; test keys unblock build; interim contact-to-pay flow already live | Open | 2026-07-20
2 | Legal/policy pages missing (PDPA Privacy, Terms, Refund, Shipping) | Compliance | High | Likely | Branny | Draft policy pages before launch; required for PDPA & Omise approval | Open | 2026-07-21
3 | Sokochan fulfilment API not yet integrated — fulfilment manual at launch | Technical | Medium | Possible | Branny | Manual fulfilment interim; schedule Sokochan integration post-MVP | Monitoring | 2026-07-21
4 | SEO & branding assets incomplete (sitemap, robots, OG tags, favicon) | Scope | Medium | Possible | Branny | Batch SEO/branding task before go-live | Open | 2026-07-21
5 | Brand name not finalized — affects domain, meta, logo, legal entity | Business | Medium | Possible | Branny | CEO to confirm final brand name | Monitoring | 2026-07-15

## Lists
DATE PICKER SOURCE LIST
Used by dropdown date-validation on other sheets — do not delete
Calendar Dates
TBD
2026-05-01
2026-05-02
2026-05-03
2026-05-04
2026-05-05
2026-05-06
2026-05-07
2026-05-08
2026-05-09
2026-05-10
2026-05-11
2026-05-12
2026-05-13
2026-05-14
2026-05-15
2026-05-16
2026-05-17
2026-05-18
2026-05-19
2026-05-20
2026-05-21
2026-05-22
2026-05-23
2026-05-24
2026-05-25
2026-05-26
2026-05-27
2026-05-28
2026-05-29
2026-05-30
2026-05-31
2026-06-01
2026-06-02
2026-06-03
2026-06-04
2026-06-05
2026-06-06
2026-06-07
2026-06-08
2026-06-09
2026-06-10
2026-06-11
2026-06-12
2026-06-13
2026-06-14
2026-06-15
2026-06-16
2026-06-17
2026-06-18
2026-06-19
2026-06-20
2026-06-21
2026-06-22
2026-06-23
2026-06-24
2026-06-25
2026-06-26
2026-06-27
2026-06-28
2026-06-29
2026-06-30
2026-07-01
2026-07-02
2026-07-03
2026-07-04
2026-07-05
2026-07-06
2026-07-07
2026-07-08
2026-07-09
2026-07-10
2026-07-11
2026-07-12
2026-07-13
2026-07-14
2026-07-15
2026-07-16
2026-07-17
2026-07-18
2026-07-19
2026-07-20
2026-07-21
2026-07-22
2026-07-23
2026-07-24
2026-07-25
2026-07-26
2026-07-27
2026-07-28
2026-07-29
2026-07-30
2026-07-31
2026-08-01
2026-08-02
2026-08-03
2026-08-04
2026-08-05
2026-08-06
2026-08-07
2026-08-08
2026-08-09
2026-08-10
2026-08-11
2026-08-12
2026-08-13
2026-08-14
2026-08-15
2026-08-16
2026-08-17
2026-08-18
2026-08-19
2026-08-20
2026-08-21
2026-08-22
2026-08-23
2026-08-24
2026-08-25
2026-08-26
2026-08-27
2026-08-28
2026-08-29
2026-08-30
2026-08-31
2026-09-01
2026-09-02
2026-09-03
2026-09-04
2026-09-05
2026-09-06
2026-09-07
2026-09-08
2026-09-09
2026-09-10
2026-09-11
2026-09-12
2026-09-13
2026-09-14
2026-09-15
2026-09-16
2026-09-17
2026-09-18
2026-09-19
2026-09-20
2026-09-21
2026-09-22
2026-09-23
2026-09-24
2026-09-25
2026-09-26
2026-09-27
2026-09-28
2026-09-29
2026-09-30
2026-10-01
2026-10-02
2026-10-03
2026-10-04
2026-10-05
2026-10-06
2026-10-07
2026-10-08
2026-10-09
2026-10-10
2026-10-11
2026-10-12
2026-10-13
2026-10-14
2026-10-15
2026-10-16
2026-10-17
2026-10-18
2026-10-19
2026-10-20
2026-10-21
2026-10-22
2026-10-23
2026-10-24
2026-10-25
2026-10-26
2026-10-27
2026-10-28
2026-10-29
2026-10-30
2026-10-31
2026-11-01
2026-11-02
2026-11-03
2026-11-04
2026-11-05
2026-11-06
2026-11-07
2026-11-08
2026-11-09
2026-11-10
2026-11-11
2026-11-12
2026-11-13
2026-11-14
2026-11-15
2026-11-16
2026-11-17
2026-11-18
2026-11-19
2026-11-20
2026-11-21
2026-11-22
2026-11-23
2026-11-24
2026-11-25
2026-11-26
2026-11-27
2026-11-28
2026-11-29
2026-11-30
2026-12-01
2026-12-02
2026-12-03
2026-12-04
2026-12-05
2026-12-06
2026-12-07
2026-12-08
2026-12-09
2026-12-10
2026-12-11
2026-12-12
2026-12-13
2026-12-14
2026-12-15
2026-12-16
2026-12-17
2026-12-18
2026-12-19
2026-12-20
2026-12-21
2026-12-22
2026-12-23
2026-12-24
2026-12-25
2026-12-26
2026-12-27
2026-12-28
2026-12-29
2026-12-30
2026-12-31
2027-01-01
2027-01-02
2027-01-03
2027-01-04
2027-01-05
2027-01-06
2027-01-07
2027-01-08
2027-01-09
2027-01-10
2027-01-11
2027-01-12
2027-01-13
2027-01-14
2027-01-15
2027-01-16
2027-01-17
2027-01-18
2027-01-19
2027-01-20
2027-01-21
2027-01-22
2027-01-23
2027-01-24
2027-01-25
2027-01-26
2027-01-27
2027-01-28
2027-01-29
2027-01-30
2027-01-31
2027-02-01
2027-02-02
2027-02-03
2027-02-04
2027-02-05
2027-02-06
2027-02-07
2027-02-08
2027-02-09
2027-02-10
2027-02-11
2027-02-12
2027-02-13
2027-02-14
2027-02-15
2027-02-16
2027-02-17
2027-02-18
2027-02-19
2027-02-20
2027-02-21
2027-02-22
2027-02-23
2027-02-24
2027-02-25
2027-02-26
2027-02-27
2027-02-28
2027-03-01
2027-03-02
2027-03-03
2027-03-04
2027-03-05
2027-03-06
2027-03-07
2027-03-08
2027-03-09
2027-03-10
2027-03-11
2027-03-12
2027-03-13
2027-03-14
2027-03-15
2027-03-16
2027-03-17
2027-03-18
2027-03-19
2027-03-20
2027-03-21
2027-03-22
2027-03-23
2027-03-24
2027-03-25
2027-03-26
2027-03-27
2027-03-28
2027-03-29
2027-03-30
2027-03-31
2027-04-01
2027-04-02
2027-04-03
2027-04-04
2027-04-05
2027-04-06
2027-04-07
2027-04-08
2027-04-09
2027-04-10
2027-04-11
2027-04-12
2027-04-13
2027-04-14
2027-04-15
2027-04-16
2027-04-17
2027-04-18
2027-04-19
2027-04-20
2027-04-21
2027-04-22
2027-04-23
2027-04-24
2027-04-25
2027-04-26
2027-04-27
2027-04-28
2027-04-29
2027-04-30
2027-05-01
2027-05-02
2027-05-03
2027-05-04
2027-05-05
2027-05-06
2027-05-07
2027-05-08
2027-05-09
2027-05-10
2027-05-11
2027-05-12
2027-05-13
2027-05-14
2027-05-15
2027-05-16
2027-05-17
2027-05-18
2027-05-19
2027-05-20
2027-05-21
2027-05-22
2027-05-23
2027-05-24
2027-05-25
2027-05-26
2027-05-27
2027-05-28
2027-05-29
2027-05-30
2027-05-31
2027-06-01
2027-06-02
2027-06-03
2027-06-04
2027-06-05
2027-06-06
2027-06-07
2027-06-08
2027-06-09
2027-06-10
2027-06-11
2027-06-12
2027-06-13
2027-06-14
2027-06-15
2027-06-16
2027-06-17
2027-06-18
2027-06-19
2027-06-20
2027-06-21
2027-06-22
2027-06-23
2027-06-24
2027-06-25
2027-06-26
2027-06-27
2027-06-28
2027-06-29
2027-06-30
2027-07-01
2027-07-02
2027-07-03
2027-07-04
2027-07-05
2027-07-06
2027-07-07
2027-07-08
2027-07-09
2027-07-10
2027-07-11
2027-07-12
2027-07-13
2027-07-14
2027-07-15
2027-07-16
2027-07-17
2027-07-18
2027-07-19
2027-07-20
2027-07-21
2027-07-22
2027-07-23
2027-07-24
2027-07-25
2027-07-26
2027-07-27
2027-07-28
2027-07-29
2027-07-30
2027-07-31
2027-08-01
2027-08-02
2027-08-03
2027-08-04
2027-08-05
2027-08-06
2027-08-07
2027-08-08
2027-08-09
2027-08-10
2027-08-11
2027-08-12
2027-08-13
2027-08-14
2027-08-15
2027-08-16
2027-08-17
2027-08-18
2027-08-19
2027-08-20
2027-08-21
2027-08-22
2027-08-23
2027-08-24
2027-08-25
2027-08-26
2027-08-27
2027-08-28
2027-08-29
2027-08-30
2027-08-31
2027-09-01
2027-09-02
2027-09-03
2027-09-04
2027-09-05
2027-09-06
2027-09-07
2027-09-08
2027-09-09
2027-09-10
2027-09-11
2027-09-12
2027-09-13
2027-09-14
2027-09-15
2027-09-16
2027-09-17
2027-09-18
2027-09-19
2027-09-20
2027-09-21
2027-09-22
2027-09-23
2027-09-24
2027-09-25
2027-09-26
2027-09-27
2027-09-28
2027-09-29
2027-09-30
2027-10-01
2027-10-02
2027-10-03
2027-10-04
2027-10-05
2027-10-06
2027-10-07
2027-10-08
2027-10-09
2027-10-10
2027-10-11
2027-10-12
2027-10-13
2027-10-14
2027-10-15
2027-10-16
2027-10-17
2027-10-18
2027-10-19
2027-10-20
2027-10-21
2027-10-22
2027-10-23
2027-10-24
2027-10-25
2027-10-26
2027-10-27
2027-10-28
2027-10-29
2027-10-30
2027-10-31
2027-11-01
2027-11-02
2027-11-03
2027-11-04
2027-11-05
2027-11-06
2027-11-07
2027-11-08
2027-11-09
2027-11-10
2027-11-11
2027-11-12
2027-11-13
2027-11-14
2027-11-15
2027-11-16
2027-11-17
2027-11-18
2027-11-19
2027-11-20
2027-11-21
2027-11-22
2027-11-23
2027-11-24
2027-11-25
2027-11-26
2027-11-27
2027-11-28
2027-11-29
2027-11-30
2027-12-01
2027-12-02
2027-12-03
2027-12-04
2027-12-05
2027-12-06
2027-12-07
2027-12-08
2027-12-09
2027-12-10
2027-12-11
2027-12-12
2027-12-13
2027-12-14
2027-12-15
2027-12-16
2027-12-17
2027-12-18
2027-12-19
2027-12-20
2027-12-21
2027-12-22
2027-12-23
2027-12-24
2027-12-25
2027-12-26
2027-12-27
2027-12-28
2027-12-29
2027-12-30
2027-12-31
2028-01-01