## REQUIREMENTS
PROJECT REQUIREMENTS
PROJECT No: | E2 |  | FULL PROJECT NAME: | Ecommerce-RaasPal
DATE: | 2026-07-09 |  | PROJECT MANAGER: | Swan Htet Aung (Branny)
REQUIREMENT LIST
ID | REQUIREMENT DESCRIPTION | REQUESTED BY | CATEGORY | PRIORITY | ACCEPTANCE CRITERIA | Status
Give each requirement a unique ID. | The feature, function, condition or capability that is required from the project, product, service or result. | The stakeholder who requested the requirement. | The category or grouping of the requirement for example: functional, technical, operational, KPI (result metric), transitional. | The priority of the requirement for example: P1, P2, P3 or MoSCoW (Must have, should have, could have, won't have). | The criteria that the requirement must have for it to be accepted by the project stakeholders. | This field describes whether the requirement is implemented or not.
1 | Homepage – Hero Banner | Khun Pom | functional | Must have | Hero banner displays headline, subtext, and CTA buttons (Find Your Ideal Robot, Book a Free Demo) above the fold; plays uploaded video when one is attached; falls back to default animation/illustration automatically when no video is set; nav menu visible below. | TRUE
2 | Homepage – Trust / About Stats ("Who We Are") | Khun Pom | functional | Should have | Displays "WHO WE ARE" eyebrow text, heading, and short about paragraph; shows 4 stat cards (500+ Robots Deployed, 4.9★ Customer Rating, 10+ Service Locations, 30 Day Returns). | FALSE
3 | Homepage – Why Choose Us | Khun Pom | functional | Should have | เ | FALSE
4 | Homepage – Popular Products | Khun Pom | functional | Must have | Displays popular/featured product cards when scrolled down; each product is clickable and navigates to its product detail page. | TRUE
5 | Homepage – YouTube CTA Section | Khun Pom | functional | Could have | Displays play icon, heading "Subscribe to RoboStore TV", subtext, and "Subscribe on YouTube" button; button links to correct YouTube channel. | FALSE
6 | Homepage – Footer | Khun Pom | functional | Must have | Displays brand block (logo, tagline "Time for Life™", copyright, social icons), Policies column (Refunds and Returns, Privacy Policy, Terms and Conditions, Shipping, Payment and Finance Options, Warranty), About column (About Us, Contact, Support, Blog, Find My Robot), and payment/trust bar with payment method badges (PromptPay, Visa, Mastercard, Amex, Bank Transfer). | FALSE
7 | Shop / product listing pages | Khun Pom | functional | Must have | _ | FALSE
8 | Product detail page | Khun Pom | functional | Must have | _ | FALSE
9 | Thai/English translation (i18n) | Khun Pom | technical | Should have | _ | TRUE
10 | Cart + Checkout | Khun Pom | functional | Must have | _ | FALSE
11 | Checkout Upsell + Standalone Installation/Demo Packages | Khun Pom | functional | Should have | Installation Service and "Request a Demo" packages are listed as regular purchasable products on the Shop/product listing page (with their own product detail page, price, and "Add to Cart" button) so customers can buy them independently at any time. Additionally, before payment is submitted during checkout, the system prompts the customer with an upsell offer relevant to the products in their cart: (a) Installation Service packages tiered by coverage area/hours (e.g. Up to 1000m² / 2.5 hrs, 2000m² / 3.5 hrs, 10000m² / 8 hrs) matched to the robot(s) added, or (b) the "Request a Demo" package. Customer can add the selected package to the cart and continue, or dismiss the prompt and proceed to payment without it; dismissing does not block checkout. | TRUE
12 | Product Recommendation feature | Khun Pom | functional | Should have |  | FALSE
13 | Contact Sales | Khun Pom | functional | Must have | Contact sales features should include a line qr of the sales team | FALSE
14 | Request Quotation | Khun Pom | functional | Should have |  | FALSE
15 | Sokochan API integration | Khun Pom | functional | Must have |  | FALSE
16 | User Profile Page | Khun Pom |  | Should have | User profile page should contain the user's address, the details of the user. | FALSE
17 | User Details Editing feature |  | operational | Should have | User profile page will have a button to edit the user details | FALSE
18 | User Address Details section |  | operational | Should have | User details page will contain the addresses the user added to his/her profile and also the editing feature of the address. | FALSE
19 | Contact Sales full function | Khun Pom | operational | Must have | User clicks contact sales button in the contact drop down at the nav bar and he should be led to a page that gives contact info about the sales team or line qr. | FALSE
20 | AI Chat | Khun Pom | functional | Could have |  | FALSE
21 | Download Brochure for each robot |  | functional | Should have |  | FALSE
22 | Light/Dark Mode | P'Chris | functional | Should have | Navy blue in dark mode and Green+White in light mode | TRUE
23 | Hero Video | Khun Pom | functional | P1 | Use video in the hero banner to display 3 robot videos in a loop. Do the | FALSE
24 | Use CI/CD |  | operational | Must have | Make use of CI/CD (Continuous Integration, Continuous Delivery/Deployment) in the project development and maintanance. | FALSE
25 | Editable product pagetempate |  | operational | Should have | Make the product page to be customizable from the admin panel by the admin. The admin should be able to fully write specification of the product the admin panel with editable content count. | FALSE
26 | Product Card Order Method |  | functional | Should have | Add drag and drop method for product card ordering in shop page. | FALSE
27 | Search Engine |  | functional | Must have | Should be able to search any products, services, and other sellable items or features that are available on the web. | FALSE
28 | Product customer review section |  | functional | Should have | A section where the customers can post reviews on products. Includes start rating, and text reviews. | FALSE
29 | [5 empty] | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## DEFINITIONS
TERM | DEFINITION
MoSCoW | A prioritization technique: Must have, Should have, Could have, Won't have.
KPI | Key Performance Indicator — a measurable value used to track a result.
P1/P2/P3 | Priority ranking, where P1 is the highest priority.

## Useful resources
RESOURCE | LINK / NOTES
Requirements gathering template | Add link here

## WebCredentials
Supabase DB | password | Raas1234@Pal
Admin Account | swan.h@raaspal.com |  | Raas1234@Pal